## Sheet1
Task | Blocker
SRS dashboard
Pendig tasks and time warnings(dasboard widget) |  | 10 hours
Chat link-SR- both web and mobile rest everyone only on web (one to one ,one to many) |  | 60 hours
Assign Contacts/leads linked to products and quality of contacts |  | 8 hours
Calendar (Outlook Integration) |  | 20 hours
Call records ( From Android phone via App) | Need api of call logs | 18 hours
SR activity with contact and assets - Activity of the lead and you need summary + Assets Activity (Shown in Phase 1 + dashboard) |  | 12 hours
Targets/actuals in number of units, customer sales (Price) and basico commission (Actuals will come from Vtiger (( contract signed) ) |  | 40 hours
Sales Conversion rates and estimation of incoming leads conversion rates (Need to get Time taken From the Lead Start date to become Customer) |  | 20 hours
show Average of the Leads Conversion rate. - Records of happening - Journey of lead conversion |  | 10 hours
Visits/opportunities-leads,prospects,opportunitys,customers- Need show data via lead status |  | 20 hours
Percentage of filled data and compare with rest of SRs (Every lead we will show bar to show data filled by SR)- Show for every leads how many fields are missing |  | 18 hours
Pending data to be filled |  | 4 hours
Mandatory fields |  | 4 hours
Platform renting follow up (Api Integration to read the data and show it in Dashboard)- Need data from Pepe |  | 12 hours
Ranking in billing amount and number of units ( Billing and sales will be compared in different SR’s and need to give them Ranking for the Best Sellers) |  | 40 hours
Logic with which you are calculating the targets _ Basico commission |  | 20 hours
Follow up in deeds- tasks which are pending (Dashboard widget) |  | 12 hours
New development- property type old vs new, rent, booking, contracts, basico commission | need more info
We need to define subtasks for them
Signature
(schedule meetings) |  | 8 hours
renting proposals (form and multiple pdf upload) |  | 8 hours
purchase proposals (form and multiple pdf upload) |  | 8 hours
renting booking (form and multiple pdf upload) |  | 8 hours
purchase booking (form and multiple pdf upload) |  | 8 hours
purchase contract(form and multiple pdf upload) |  | 8 hours
renting contract (form and multiple pdf upload) |  | 8 hours
purchase deed(form and multiple pdf upload) |  | 8 hours
renewal(form and multiple pdf upload) |  | 8 hours
novation(form and multiple pdf upload) |  | 8 hours
renting booking settelment(form and multiple pdf upload) |  | 8 hours
purchase booking settelment(form and multiple pdf upload) |  | 8 hours
renting contract settlement(form and multiple pdf upload) |  | 8 hours
purchase contract settlement(form and multiple pdf upload) |  | 8 hours
8 hours
Regional manager dashboard
Summary SRs targets/actuals(dasboard widget) |  | 8 hours
Regional/National ranking(dasboard widget) |  | 8 hours
SRs data pending to be filled and done(dasboard widget) |  | 8 hours
Targets per promotion/portfolio/products(dasboard widget) |  | 8 hours
Time warnings from platform and tasks- SRS I should know instances(dasboard widget) |  | 10 hours
Direct access to SRs and clients activities(dasboard widget) |  | 8 hours
Portfolio manager dashboard
Time warnigs |  | 8 hours
Contacts/visits/sales conversion rates |  | 8 hours
Target/actuals portfolio |  | 8 hours
Sales director dashboard
Renovation status |  | 8 hours
Portfolio/region summary |  | 8 hous
Target/actuals region/portfolio |  | 16hours
Pending operations to be commissioned |  | 8 hours
Totals summary |  | 8 hours
Call center/commercial support view ( Phase 3)
CEO Dashboard |  | 40 hours
Company aggregate (mostly commercial view) |  | 20 hours
Promotions, Portfolios, Assets. |  | 20 hours
Valuations ( Phase 3)
Finance (Phase 3)
collections ( Phase 3)
Regional admin Dashboard
Need to confirm
Total hours |  | 650 hours