## Hoja1
Task Number | Task description | Owner | Deadline | Comments
1 | Registration and login: Implementation of C and SP registration in duda. The C and SP are different registration with different fields. We needs the integration of registration in the different platform (duda, Amelia, BBB) with only one registration process for SP and one for C. The SP and C login after the registration, the access will be with mail and password created in the registration. Each one access to its personal space. | BizTechNosys |  | Pending the date
2 | Integration of Duda, Amelia and BBB. Duda is the front-end of SPs and C. Amelia is the booking platform. BBB is the platform for sessions. We need the the implementation of the integration of the three platform in order to implement the duda flow document sent. | BizTechNosys
3 | Payment Process and session discount. We need the implementation of payment process accroding to the document sent. | BizTechNosys |  | Pending the date
4 | The web experience need to be responsive, working fine in mobile devices, tablet with Android and IOS and the different navigator at least in its last versions (iexplorer, Edge, Firefox,Chrome…). We need usability tests to check the usability is OK in the different devices with different last releases. If some problem appear we need to fix them. This task needs to tests all the flow sent with the different devices. | BizTechNosys |  | Pending the date. BizTechNosys needs to do these tests and after it will be repeated by Pedro.
5 | Security tests to assure that we are not going to have problems with at least: -DoS attach. Need to implement reCAPTCHA v2 or reCAPTCHA v3. - Security in the SP and C data with secure programming. - Security of interfaces implementation and architecture of the solution. Except reCATCHA implemention that was requested yet, the security tests for us is including in the secure development implemented by BizTechNosys and it is not an extra work requested. | BizTechNosys |  | Pending date.
6 | Deployment in production after UAT tests made by BizTechNosys and Pedro |  |  | Pending date.